## 00 Test Plan
Section | Details
Project | Knight's Blvd Retail Management System - V1
Testing Objective | Verify that the application's core retail functions operate correctly and that data is stored and retrieved reliably.
Testing Type | Functional Testing, Integration Testing, Data Persistence Testing, Negative Tesing, Regression Testing.
Application Area | Product management, customer management, order processing, sales records, database operations and application exit.
In Scope | View Products; Add Product; Search Product; Update Product; Remove Product; View Customers; Place Order; Stock Validaion; Quantity Validation; View Sales; Database Persistence; Application Exit.
Out of Scope | Payment gateway integration, online deployment, multi-user concurrency, security penetration testing and production-scale performance testing.
Test Enviroment | Windows 11 Laptop, Python application, SQLite adatabase, local execution.
Test Data | Products, customers, stock quantities, orders and sales records created during testing.
Entry Criteria | Application launches successfully and required Python/SQLite components are available.
Exit Criteria | Planned test cases executed, identified defects fixed or ducumented, and retests completed.
Defect Handling | Defects recorded with reproduction steps, expected/actual results, severity, root cause, fix and retest status.
Evidence | Screenshots and evidence records linked to relevant test cases and retests.
Overall Result | All planned V1 test cases passed after identified defects were corrected and retested.

## 01 Test Cases
Test Case ID | Test Area | Test Case | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Evidence ID | Evidence Description
TC-001 - View Products | Products | Verify that the user can view products stored in the system. | Application is running and products exist in the database. | Launch application, Select 1. View Products | Existing products | Products are displayed with their relevant details. | Products displayed succesfully. | PASS | Screenshot 2026-09-18 155359.png | Screenshot showing the product list displayed successfully.
TC-002 - Add Product | Products | Verify that the user can add a new product to the system. | Application is running and the product does not already exist. | Select 2. Add Product, enter the product details, submit the product. | A new product with valid name, size, price, color, style and stock. | Product is successffully added and appears in the product inventory. | New product is added successfully. | PASS | Screenshot 2026-09-18 155516.png / Screenshot 2026-09-18 155625.png | Screenshot showing the new project successfully added and displayed in inventory.
TC-003 - Seaarch Product | Products | Verify that the user can search for an existing producr by name. | Application is running and the product exists in the database. | Select 3. Search Products, enter an existing product name - submit the search | An existing product, e.g. Black Hoodie. | The matching product is found and its details are displayed correctly. | Product details displayed successfully. | PASS | Screenshot 2026-09-18 155717.png | Screeenshot showing the search being perrformed and matching product details displayed.
TC-004 - Update Product | Products | Verify that the user can update the details of an exisitng product. | Application is running and the product exists in the database. | Select 8. Update Product, enter an existing updated product datails, save changes. | Existing product with modified details. | Product details are successfully updated and the new information is displayed. | Successful update message. | PASS | Screenshot 2026-09-18 155625.png / Screenshot 2026-09-18 160549.png | Screenshot showing the product before/after the update and the successful update message.
TC-005 - Update Persistence | Database / Products | Verify that updated product information persists after restarting the application. | A product has been successfully updated. | Update a product, close the application, restart the application, view/search the product. | The product updated during TC-004. | The updated product details remain unchanged after restarting the application |  | PASS | Screenshot 2026-09-18 155717.png | Screenshot showing the updated product after restarting the application.
TC-006 - Remove Product | Products | Verify that the user can remove an existing product from the system. | Application is running and the product exists in the database. | Select 9. Remove Product, enter an existing product name, confirm removal. | An existing product intended for removal. | The product is successfully removed and no longer appears in the product inventory. | The updated product shows after restarting the application. | PASS | Screenshot 2026-09-18 160736.png | Screenshot showing the product removal and confirmation that it was removed.
TC-007 - Remove Persistence | Database / Products | Verify that a removed product remains absent after restarting the application. | A product has been successfully removed. | Remove a product, close the application, restart the application, view/search the product. | The product removed during TC-006. | The removed product does not reappear after the application is restarted. | The removed product remains absent after restart the application. | PASS | Screenshot 2026-09-18 160914.png | Screenshot showing that the removed product remains absent after restarting the application.
TC-008 - Add Customer | Customer | Verify that the user can add a new customer to the system. | Application is running and the customer does not already exist. | Select 4. Add Customer, enter valid customer details, submit the customer. | New customer's name and email address. | Customer is successfully added and stored in the database. | The customer being successfully added. | PASS | Screenshot 2026-09-18 155832.png | Screenshot showing the customer being successfully added.
TC-009 - View Customer | Customers | Verify that the user can view customers stored in the system. | Application is running and at least one customer exists in the daatabase. | Select 7. View Customer, review the displayed customer list. | Existing customers in the database. | The system displays the stored customers and their relevant details correctly. | The customer list displayed by the system. | PASS | Screenshot 2026-09-18 160225.png | Screenshot showing the customer list displayed by the system.
TC-010 - Place Order | Orders | Verify that the user can successfully place an order for an existing customer and available product. | Application is running; customer exists; product exists; sufficient stock is available. | Select 5. Place Order, enter customer, enter product, enter valid quantity, confirm order. | Customer: Bhlomingtn; Product: Black Hoodie; Quantity: 2 | Order succesfully processed, receipt/order details are generated, and the transaction is recorderd. | Succesful order/receipt showing customer, product, quantity, price and total. | PASS | Screenshot 2026-09-18 160031.png | Screenshot of the successful order/receipt showing the customer, product, quantity, price and total.
TC-011 - Insufficient Stock | Orders / Inventory | Verify that the system prevents an order when the requested quantity exceeds available stock. | Application is running; customer exists; product exists; product has limited stock. | Select 5. Place Order, select customer, select product, enter a quantity greater than availble stock, submit order. | Grey Beanie - request 10 when only 8 are available. | The order is rejected and system informs the user that there is insufficient stock. Inventory is not reduced incorrectly. | Insufficient stock message and rejected order. | PASS | Screenshot 2026-09-18 181940.png | Screenshot showing the insufficient-stock message and rejected order.
TC-012 - Invalid Quantity | Invalid Validation / Orders | Verify that the system rejects invalid order quantities. | Application is running; customer and product exist. | Select 5. Place order, enter customer/product, enter an invalid quantity such as 0 or non-numeric text, submit | Invalid input and the resulting validation message. | Screenshot showing the invalid input and the resulting validation message. | Quantity must be greater than zero. / Invalid quantity. Please enter a number. | PASS | Screenshot 2026-09-18 181447 / Screenshot 2026-09-18 181611.png / Screenshot 2026-09-18 181809.png | Screenshots showing invalid quantity or invalid validation message.
TC-013 - View Sales | Sales | Verify that the user can view recorderd sales transactions. | Application is running and at least one successful order exists. | Select 6. View Sales, review the displayed sales records. | Previously completed Black Hoodie order. | The system displays recorderd sales with the relevant customer, product, quantity, total and transaction details. | Record sales displayed correctly. | PASS | Screenshot 2026-09-18 160122.png | Screenshot showing the recorderd sale displayed correctly.
TC-014 - Database Persistence | Database | Verify that application data is retained after closing and restarting the application. | Products, customers and/or sales have been successfully stored in the system. | Add/update/store data, close the application normally, restart the application, check the stored data. | Previously created or updated product/ customer/sale records. | Previously saved data remains available after restarting the application. | Previously saved data still available after application restart. | PASS | Screenshot 2026-09-18 182224.png | Screenshot showing previously saved data still available after application restart.
TC-015 - Application Exit | Application / Stability | Verify that the application exists normally without producing an error. | Application is running. | Launch the application, Select 10. Exit, observe the application reponse. | Exit option 10. | The application closes normally without displaying an error or traceback. | Normal application exit. | PASS | Screenshot 2026-09-18 160811.png | Screenschot showing the application exit message/normal termination, if available.

## 02 Test Execution
Test Case ID | Test Date | Test Performed | Test Data | Expected Result | Actual Result | Status | Tester Notes | Evidence ID
TC-001 | 14/09/2026 | Viewed products using option 1. | Existing products | Products are displayed with their relevant details. | Describe exactly what you observed. | PASS | Any useful observation
TC-002 | 14/09/2026 | Added a new product using option 2. | New product with valid product details. | Product is successfully added and appears in the product inventory. | Product was successfully added and appeared in the inventory. | PASS | Valid product data was accepted and the product was stored successfully.
TC-003 | 14/09/2026 | Searched for an existing product using option 3. | Black Hoodie | The matching product is found and its details are displayed correctly. | Initially, the search produced an AttributeError because the reurned database record was atuple while the code expected a product object. The search/display logic was corrected to use the tuple values. The search was then tested again and worked correctly. | PASS | Defect identified and corrected. Successful retest confirmed the search function works are expected.
TC-004 | 14/09/2026 | Updated an existing product using option 8. | Existing product with modified product details. | Product details are successfully updated and new information is displayed. | Product was successfully added and the updated details were displayed. | PASS | Update function was tested successfully.
TC-005 | 14/09/2026 | Restarted the application after updating a product and checked the product again. | Product updated during TC-004. | Updated product information remains unchanged after the restarting the application. | The updated product information remained saved and was still present after restarting the application. | PASS | Confirms that product updates persist in the SQLite database.
TC-006 | 14/09/2026 | Rmoved an existing product using option 9. | Existing product selected for removal. | Product is successfully removed and no longer appears in the product inventory. | Product was successfully removed and no longer appeared in the inventory. | PASS | Product removal function worked as expected.
TC-007 | 15/09/2026 | Restarted the application after removing a product and checked the product inventory. | Product removed during TC-006. | The removed product remains absent after restarting the application. | The removed product remained absent after restarting the application. | PASS | Confirms that product removal is persisted in the SQLite database.
TC-008 | 15/09/2026 | Added a new customer using option 4. | New customer with a valid name and email address. | Customer is successfully added and stored in the database. | Customer was successfully added and stored in the system. | PASS | Valid customer information was accepted successfully.
TC-009 | 15/09/2026 | Viewes the stored customers using option 7. | Existing customers in the database. | The system displays the stored customers and their relevant details correctly. | The customer list was displayed successfully, including customers previously added on the databsae. | PASS | Customer records were successfully retrieved and displayed.
TC-010 | 15/09/2026 | Placed an order using option 5 for an existing customer and product. | Customer: Bhlomingtn; Product: Black hoodie; Quantity: 2; Unit price: R799,99 | Order is successfully processed. Receipt/order details generated, and the transaction is recorderd. | Order was successfully processed. A receipt was generated showing Black Hoodie x2, with a total of R1,599.98 and a successful transaction status. | PASS | Successful end-to-end order transaction verified.
TC-011 | 15/09/2026 | Attempted to place an order for more units than were available in stock. | Grey Beanie - requested 10, available 8. | Order is rejected and the system informs the user that there is insufficient stock. | The system detected that the requested quantity exceeded available stock and prevented the order from being completed. | PASS | Stock validation prevented an invalid transaction.
TC-012 | 15/09/2026 | Attempted to place orders using invalid quantities. | Quantity 0 and non-numeric input. | The system rejects invalid quantities,displays an appropiate validation message, and does not crash. | Quantity 0 produced "quantity must be greater than 0". Non-numeric input produced "Invalid quantity. Please enter a number." | PASS | Both invalid-input scenarios were handled correctly without completing an invalid order.
TC-013 | 15/09/2026 | Viewed recorded sales using option 6. | Previously completed Black Hoodie sale. | Recorded sales are displayed with relevant customer, product, quantity, and total. | The sales recorrds were successfully displayed after the sales-handling issue was corrected. | PASS | A sales display defect was previously identified and corrected. Successful retesting confirmed the function works correctly.
TC-014 | 15/09/2026 | Restarted the application and verified previously saved data remained available. | Previously saved product, customer and transaction data. | data remains available after the application is closed and restarted. | Previously saved data remained available after restarting the application. | PASS | Confirms that stored application data persists through an application restart.
TC-015 | 15/09/2026 | Seleected option 10. Exit to close the application. | Exit option 10 | Application closes normally without displaying an error or traceback. | Application exited normally without displaying an error. | PASS | Normal application termination verified.

## 03 Defect Log
Defect ID | Related Test Case | Defects Summary | Steps to Reproduce | Expected Result | Actual Result | Severity2 | Root Cause | Fix Applied | Status | Retest Required
BUG-001 | TC-015 | Application attempted to access the database after the database connection had been closed. | Run the application, exit/close the database connection, execute the remaining obsolete database operation. | Application should terminate normally without attempting to use a closed database connection.` | Application produced sqlite3.ProgrammingError: Cannot operate on a closed database. | High | Obsolete code remained after the menu/database flow had been changed and attempted to load products after the database connection was closed. | Removed the obsolete database/ product-loading code so the application no longer performs database operations after closing the connection. | Fixed | Yes
BUG-002 | TC-003 | Product Search attempted to access a database tuple as if it were an Product object. | Run the application, select 3. Search Products, enter an existing product name. | Matching product is found and its details are displayed correctly. | Application produced AttributeError: 'tuple' object has no attribute 'name'. | Medium | Database records were returned as tuples, while the search/display code attempted to access Product object attributes such as .name. | Updated the search and display logic to use the correct tuple indexes, such as product[0] for the product name. | Fixed | Yes
BUG-003 | TC-013 | View Sales encountered an error because sales record fields were not being handled/displayed correctly. | Run the application, select 6. View Sales, attempt to display recorded sales. | Recorded sales should display correctly, including customer. Product, quantity and total. | Sales Display initially failed because expected sales fields contained incorrect/None values, causing an error. | High | Sales tuple fields/indexes were being interpreted incorrectly when the sales records were retrieved. | Corrected the sales data handling/display logic so the correct fileds are retrieved and displayed. | Fixed | Yes
BUG-004 | TC-002 | Duplicate product handling required validation to prevent an existing product from being added again. | Run the application, select 2. Add Product, enter the name of an existing product, such as Black Cargo Pants, submit. | Sytem should reject the duplicate product and display a clear message without crashing. | System detected that the product already existed and displayed: Product Black Cargo Pants already exists in the database. A subsequemt test exposed an additional error during the handling flow, which was corrected. | Medium | Duplicate-product validation/error handling was not fully handled correctly in the application flow. | Corrected the duplicate-product handling so the existing product is rejected safely rather than causing the application to crash. | Fixed | Yes
BUG-005 | TC-012 | Invalid quantity input required validation to prevent invalid orders. | Select 5. Place Order, enter an invalid quantity such as 0 or non-numeric text. | Invalid quantity should be rejected with a clear validation message without crashing. | The system rejected 0 with "quantity must be greater than 0" and rejected non-numeric input with "Invalid quantity. Please enter a number." | Low | Input validation was required to handle invalid quantity values safely. | Quantity validation was implemented/corrected to reject zero abd non-numeric values. | Fixed | Yes

## 04 Retest Results
Retest ID | Defect ID | Original Test Case | Retest steps | Expected result | Actual result | Status | New Evidence ID | Tester Notes
RET-001 | BUG-001 | TC-015 | Run the application, perform normal operations, select 10. Exit. | Application exits normally without attempting to use a closed database connection. | Application exited normally without the Cannot operate on a closed database error. | PASS |  | Obsolete database operation was removed and the application was successfully retested.
RET-002 | BUG-002 | TC-003 | Run the application, select 3. Search Products, enter an existing pproduct name. | Matching product is found and its details are displayed correctly without an error. | Product search successfully found and displayed the matching product after the tuple-handling correction. | PASS |  | Search functionality was successfully retested after correcting the tuple/object handling issue.
RET-003 | BUG-003 | TC-013 | Run the application, select 6. View Sales, review the recorded message | Sales records display correctly with the customer, product, quantity and total. | Sales records displayed successfully after the sales data-handiling correction. | PASS |  | Sales functionality was successfully retested after correcting the sales record handling.
RET-004 | BUG-004 | TC-002 | Run the application, select 2. Add Product, enter the name of an existing product, submit the product. | Duplicate product is rejected with a clear message and the applicaction does not crash. | The system detected the existing product and displayed the duplicate-product message without allowing the duplicate to be added. | PASS |  | Duplicate-product handling successfully retested after the correction.
RET-005 | BUG-005 | TC-012 | Run the application, select 5. Place Order, enter an valid customer/product, test quantity 0, repeat using non-numeric input. | Invalid quantities are rejected with clear messages and the application does not crash. | Quantity 0 was rejected with "quantity must be greater then 0". Non-numeric input was rejected with "Invalid quantity. Please enter a number." | PASS |  | Both invalid-input scenarios passed successfully during retesting.

## 05 Evidence Index
Evidence ID | Evidence Type | Related Test Case | Related Defect | Evidence Description | What it proves | File/ Screenshot Name | Retest Evidence
EV-001 | Screenshot | TC-001 |  | Main Knight's Blvd application menu displaying the available system functions. | Confirms that the application launches successfully and presents the availlable functions to the user. | Screenshot 2026-09-18 155359.png | No
EV-002 | Screenshot | TC-001 / TC-002 |  | Screenshot showing products displayed in Knight's Blvd inventory. | Confirms that existing products can be displayed and that a successfully added product can appear in the inventory. | Screenshot 2026-09-18 155516.png / Screenshot 2026-09-18 155625.png | No
EV-003 | Screenshot | TC-003 | BUG-002 | Screenshot showing a product being searched and the matching product details displayed. | Confirms that product search works correctly after the object handiling defect was fixed. | Screenshot 2026-09-18 155717.png | Yes - supports RET-002
EV-004 | Screenshot | TC-004 |  | Screenshot showing the product update process and the updated product details. | Confirms that an existing product can be updated successfully. | Screenshot 2026-09-18 160549.png | No
EV-005 | Screenshot | TC-005 |  | Updated product details displayed after restarting the application. | Confirms that product updates are saved to the database and persist after application restart | Screenshot 2026-09-18 155717.png | No
EV-006 | Screenshot | TC-006 |  | Product successfully removed from the inventory. | Confirms that an existing product can be removed from the database an no longer appears in the inventory. | Screenshot 2026-09-18 160736.png | No
EV-007 | Screenshot | TC-007 |  | Removed product remains absent after restarting the application. | Confirms that product removal is permanently saved to the database and persists after application restart. | Screenshot 2026-09-18 160914.png | No
EV-008 | Screenshot | TC-008 |  | New customer successfully added to the system. | Confirms that the application can accept and store a new customer record. | Screenshot 2026-09-18 155832.png | No
EV-009 | Screenshot | TC-009 |  | Customer records displayed in the application. | Confirms that saved customer records can be retrieved and displayed successfully. | Screenshot 2026-09-18 160225.png | No
EV-010 | Screenshot | TC-010 |  | Successful customer order and receipt generated for Black Hoodie. | Confirms that a customer order can be processed successfully, inventory stcok can be deducted, and a receipt can be generated with transaction details. | Screenshot 2026-09-18 160031.png | No
EV-011 | Screenshot | TC-011 |  | Order prevented when requested quantity exceeded available stock. | Confirms that the system correctly checks available inventory and prevents an order when there is insufficient stock. | Screenshot 2026-09-18 181940.png | No
EV-012 | Screenshot | TC-012 | BUG-005 | Invalid order quantities rejected with appropiate validation message | Confirms that zero and non-numeric quantities are rejected without crashing the application. | Screenshot 2026-09-18 181447 / Screenshot 2026-09-18 181611.png / Screenshot 2026-09-18 181809.png | Yes - supports RET-005
EV-013 | Screenshot | TC-013 | BUG-003 | Sales records displayed successfully in the application. | Confirms that completed sales transactions can be retrieved and displayed correctly after the sales-handling issue was fixed. | Screenshot 2026-09-18 160122.png | Yes - supports RET-003
EV-014 | Invalid quantity validation | TC-014 |  | Saved products, customers, and transaction data remain available after restarting the application. | Confirms that important application data is stored persistently in the SQLite database rather than existing only during the current session. | Screenshot 2026-09-18 182224.png | No
EV-015 | Database persistence | TC-015 | BUG-001 | Application exits normally without producing a database connection error. | Confirms that the closed-database defect was resolved and the application can terminate normally. | Screenshot 2026-09-18 160811.png | Yes - RET-001

## 06 Test Summary
Metric | Result | Notes
Total Test Cases | 15 | TC-001 to TC-015
Passed Test Cases | 15 | All executed test cases passed after fixes
Failed Test Cases | 0 | No unresolved test failures
Defects Identified | 5 | BUG-001 to BUG-005
High Severity Defects | 2 | BUG-001 and BUG-003
Medium Severity Defects | 2 | BUG-002 and BUG-004
Low Severity Defects | 1 | BUG-005
Defects Fixed | 5 | All identified defects were corrected
Retests Performed | 5 | RET-001 to RET-005
Retests Passed | 5 | All fixes passed retesting
Evidence Records | 15 | EV-001 to EV-015
Overall V1 Result | PASS | Core tested functionality is operational