## Test Summary
KNIGHT'S BLVD - QA / TESTING EVIDENCE WORKBOOK
Project | Knight's Blvd Retail Mangement System
Evidence basis | Retrieved project files, source-code evidence and previously recordeedtest outcomes
Workbook purpose | Portfolio-ready record of functional testing, defects, fixes, and supporting evidence
Test recorded | 12
PASS | 8
FAIL/BUG | 4
Evidence note | Screenshot filenames are referenced where known; additional screenshots can be added

## Test Cases
Test ID | Test Name | Type | Test Input | Expected Outcome | Actual Outcome | Status | Evidence | Notes
TC-001 | View Products | Functional | Select option 1/ View Products | Stored products should be displayed in inventory. | Products were displayed after product data wass available. | PASS | main.py/ store.py | Product display functionality evidenced in code.
TC-002 | Add Products | Functional | Enter product details and submit a new product. | New product should be added to inventory/database. | New Black Hoodie product appeared in inventory after being added. | PASS | main.py | Observed test outcome from project work.
TC-003 | Search Product by Name | Functional | Search for a existing product by name. | Matching product should be returned. | Existing product serach returned the expected product during | PASS | main.py/ inventory.py | Search function was tested during development.
TC-004 | Search Product - not found | Negative | Search for a product that is not present. | System should report product not found without | Non-matching search produced the not-found path during | PASS | main.py/ inventory.py | Negative search scenario.
TC-005 | Duplicate Product | Validation | Attempt to add an existing product | Duplicate should be rejected with a clear message and | System displayed: Product Black Cargo Pants already exists in | FAIL/BUG | main.py | Duplicate habdling exists in code, but one observed
TC-006 | Add Existing Customer | Validation | Aattempt to add a customer already stored in | Duplicate customer should be rejected clearly. | Existing customer was already present; duplicate-check logis is | PASS | main.py/ database.py | Code evidence supports duplicate prevention.
TC-007 | Invalid Quantity - text input | Negative | Enter a non-numeric quantity while placing order | System should reject input and explain that quantity | Received: Invalid quantity. Please enter a number. | PASS | main.py/ order flow | Observed expected outcome.
TC-008 | Invalid Quantity - zero/negative | Negative | Enter quantity <=0. | System should reject quantity. | Store logic explicitly checks quantity <= 0 and prints Quantity | PASS | store.py | Source-code evidence.
TC-009 | Insufficient Stock | Negative | Request more units than available stock. | Sale should be rejected and available stock shown. | Store logic checks stock and reports insufficient stock when | PASS | store.py | Source-code evidence.
TC-010 | Place Order / Checkout | Functional | Use customer, product and quantity to place an order. | Order should calculate total and complete checkout. | Order examples include successful checkout flow and receipt | PASS | main.py/ order.py/ receipt.py | Project test evidence.
TC-011 | Database Persistence | Database | Load products/ customers from database and store | Records should be loaded/saved without data loss. | main.py loads products and datbase checks are used before | PASS | main.py/ database.py | Source-code evidence.
TC-012 | Database / Runtime Defects | Reliabilty | Run application through repeated | Application should not crash due to database | Multiple runtime defects were encountered during development, | FAIL/BUG | database.py/ main.py/ store.py | Historical defect evidence retained for QA record.

## Bug Log
Bug ID | Defect | Category | Reproduction/ Trigger | Expected | Observed | Status | Related Test | Evidence
BUG-001 | Duplicate product handling | Validation | Adding already existing Black Cargo Pants | Application should reject duplicate and continue | Duplicate message was produced, but a ValueError/crash was | Open/ Needs verification | TC-005 | main.py duplicate-check path
BUG-002 | Database path / file acces | Database | Run application after kb.db was moved. | Application should locate/ open its configured | Encountered sqlite3.OperationalError: uable to open database | Historical defect | Development Log | Database location issue was
BUG-003 | Closed database connection | Database | Continue using database after close operation. | Application should not operate on a closed | Encountered ProgrammingError: Cannot operate on a closed | Historical defect | Development Log | Connection lifecycle issue.
BUG-004 | Data type / formatting errors | Runtime | Display sale records and timestamps. | Values should use compatible formatting/types. | Encountered unsupported format string and str has no attribute | Historical defect | Development Log | Timestamp handling issue.
BUG-005 | Product object mismatch | Runtime | Load products and use them as Product objects. | Loaded records should expose Product | Encountered AttributeError: tuple object has no attribute name. | Historical defect | Development Log | load_products return/ object conversation
BUG-006 | SQL syntax | Database | Create database tables. | Tables should be created without SQL errors. | Encountered OperationalError near AUTOINCREMENT and near | Historical defect | Development Log | Schema/SQL syntax defects.

## Validation Tests
ID | Validation Scenario | Input | Expected | Actual | Status
VAL-001 | Non-numeric quantity | abc | Invalid quantiy. Please enter a number. | Invalid quantity. Please enter a number. | PASS
VAL-002 | Zero quantity | 0 | Quantity must be greater than zero. | Sourcee code contains quantity <= 0 validation. | PASS
VAL-003 | Negative quantity | -1 | Quantity must be greater than zero. | Source code contains quantity <= 0 validation. | PASS
VAL-004 | Duplicate product | Black Cargo Pants | Existing product should be rejected. | Duplicate message observed: crash also observed in one run. | FAIL/BUG
VAL-005 | Duplicate customer email | Existing email | Existing customer should be rejected. | customer_exists(email) check is implemented. | PASS
VAL-006 | Insufficient stock | Quantity greater than available | Sale should be rejected with available stock. | Insufficient-stock branch is implemented. | PASS

## Order Evidence
Evidence ID | Order ID | Customer | Product | Qty | Unit Price ® | Total ® | Evidence | Status
ORD-001 | ORD001 | Bhlomingtn | Black Hoodie | 2 | 799.99 | 1,599.98 | Successful order/receipt evidence recorderd. | PASS
ORD-002 | ORD002 | Bloom Pot | Black T-Shirt | 2 | 299.99 | 599.99 | Order object and display_order example present in | PASS
ORD-003 | ORD003 | Bhlom Doe | Black Cargo Pants | 2 | 799.99 | 1,599.98 | Order object example present in main.py | PASS
ORD-004 | ORD004 | John Raven | Black Denim Jeans | 2 | 799.99 | 1,599.98 | Order object example present in main.py | PASS
ORD-005 | ORD005 | Jane Smith | Black Shirt | 2 | 399.99 | 799.99 | Order object example present in main.py | PASS
ORD-006 | ORD006 | Jane Doe | Black Sweater | 2 | 599.99 | 1,199.98 | Order object example present in main.py | PASS
ORD-007 | ORD007 | Bonnie Doe | Black Windbreaker | 2 | 799.99 | 1,599.98 | Order object example present in main.py | PASS
ORD-008 | ORD008 | Late Blvd | Black Bomber Jacket | 2 | 999.99 | 1,999,98 | Order object example present in main.py | PASS

## Database Evidence
ID | Area | Evidence | Source | Status
DB-001 | Database initialization | Database() and create_tables() are called at application startup. | main.py lines 19 - 22 | PASS
DB-002 | Product persistence | product_exist() is checked before save_product(). | main.py lines 55 - 59 | PASS
DB-003 | Customer persistence | customer_eists(email) is checked before save_customer(). | main.py lines 78 - 82 | PASS
DB-004 | Product loading | load_products() is used to populate inventory. | main.py lines 109 - 111 | PASS
DB-005 | Sales persistence | sell_product() calls db.save_sale() with customeer, product, quantity and total_price. | store.py lines 450 - 456 | PASS
DB-006 | Stock update | db.update_stock() is invoked for order products in the project data flow. | main.py | PASS

## Evidence Index
Evidence ID | Source | Evidence Type | What it Supports | Related Area
EV-001 | main.py | Source code | Application menu: View Products, Add Products, Search Product, Add Customer, Place Order, Exit. | Functional scope evidence
EV-002 | main.py | Source code | Duplicate product and duplicate customer cheks. | Validation evidence
EV-003 | main.py | Source code | Quantity validation, stock validation, total calculation and sale saving. | Order/validation evidencce
EV-004 | main.py | Source code | Order examples including OR001 and multiple product/customer records. | Order evidence
EV-005 | Knight's Blvd Signature Set Ideas.png | Brand asset | Knight's Blvd visual identityand signatue set concepts. | Project context
EV-006 | Knight's Blvd brand identity guide.png | Brand asset | Brand identity guide showing shield, sword, KB, crown and garment applicaations. | Project context
EV-007 | 48 logo concepts for Knight's Blvd.png | Brand asset | 48 logo concept explortion sheet. | Project context
EV-008 | 48 icons of progression.png | Brand asset | 48 collection progresssion icon concepts. | Project context
EV-009 | Observed test result | Manual test evidence | Invalid quantity produced: Invalid quantity. Please enter a number. | Validation test TC-007
EV-010 | Observed test result | Manual test evidence | Duplicate Black Cargo Pants message was produced; one run then crashed with | Bug/validation TC-005
EV-011 | Observed receipt | Manual test evidence | Order OR001: Black Hoodie, qty 2, unit price R799.99, total R1599,98. | Order/receipt TC-010

## Progress Log
Date | Sprint | Work Area | Activity | Outcome
2026-09-06 | Sprint 5 | Database / sales | Worked through sale records, stock updates, timestamps and | Database defects identified and documented.
2026-09-07 | Sprint 5 | QA documentation | Organised project evidence and testing records for portfolio | QA evidence structure establised.
2026-09-09 |  | QA workbook | Compiled retrieved source-code and test evidence into workbook. | Workbook created.

## Final QA Summary
Area | Assessment | Status
Core menu / navigation | Main application contains the primary retail management menu and routes for products, customerrs and | PASS
Product management | Products can be added, loaded and checked for duplicates; search functionality is represented in the | PASS
Customer management | Customer duplicate checking by email is implemented. | PASS
Porder processsing | Order creation, quality checks, stock checks, total calculation and sale persistence are represented. | PASS
Database | SQLite persistence is intergrated, but historical connection/path defects were encountered | PASS WITH HISTORICAL
Input validation | Invalid quality and stock conditions have validation paths; duplicate-product handling needs final | PARTIAL
Overall QA position | The project has substantial functional evidence and a documented defect history. Final regression should | PARTIAL/ REGRESSION NEEDED